## Sheet2
Reset Dates:
RESET PREPARATION CHECK SHEET
The purpose of this reset checklist is to ensure that your store has properly met deadlines and completed all tasks below. These task are very important.
They will ensure your reset goes on schedule and minimize downtime. It is imperative that your store reopen for business on time after the reset. Make sure all
suspense's dates are met and completed tasks are email to the Sales Directorate Reset Program Manager that is assisting you with your store reset.
Some of your suspense dates will need to be met in advance and others met up to the day of the reset. Detailed information can be found in "Guide to Resets".
|  |  | *PLEASE READ GUIDES PRIOR TO STARTING THE CHECK SHEET* |  |  | 2016-01-24
|  |  |  | RESET TASK | SUSPENSE DATE | COMPLETION DATE
(SAVE) Boxes, Pallets, Milk Crates, Produce Dump Bins (50 pallets of boxes) *Shrink Wrapped*
2,500 milk crates(For pull down), 300 pallets for shelving change out, unlimited boxes and produce bins, milk bossies
Store Sell Down | *PLEASE SELL DOWN THE STORE, BUT NOT OUT*
HBC ramped down E's-F's 10% four wks. out / C's-D's 10% two wks. out.
Coordinate store closing (CLOSE @ 4 P.M. PRIOR TO ON SUNDAY PULL DOWN)
Notify installation, post info in store, newspaper, website, store recording, use(Commissary reset improves flyer guide)
Coordinate scheduling of employees * Confirm with Reset Specialist at Conference Call*
Pull down of product / Restocking of product / Pulling ESL's - Rails / Reinstalling ESL's - Rails
Frozen and Chill shelving for reset. POC. Linda Lopez
ESL's Rails for Dry, Frozen, Chill Dairy and Lunchmeat. POC. Cynthia Simons / James Beach
Mode for CA contract / Schedule for contractors
300 - 400 hrs. needed approval Zone Mgr. - Contractor Officer
Coordinate with national vendors on equipment
Magna Bars, Deodorant Rack, Hosiery Rack, Skilcraft Hooks, Coolers, Hooks
Order new ESL's rails for new sections (gondolas) and or to replace damaged rails (wire rails are different) scanner peg rails
POC: Cynthia Simons/James Beach
Coordinate with contractor shelving installer for personal to entering post
Approval from post security |  | *Installer will contact the store*
Schedule electrician to disconnect/reinstall any power outlets in gondolas
Dates and times needed (Fresh Pet Cooler, conduit attached to shelving)
Coordinate with HQ and Zone Mgr., for early*Price Changes* if reset is scheduled during price changes
(POC) Zone Mgr. / John Madar (Store Ops) |  |  |  | Request early price changes if needed, Pending RESET DATES
(IF APPLICABLE)
Verify store final layout with Sales Directorate
Disposal of old shelving
(POC) Billy Guyton, Supply Technician 804-734-8000 x48341
Scheduling of in store lunch with ALA representative (for reset two days)
Coordinate with local (DSD) vendors and merchandisers of reset and equipment needed
Dates and times
Equipment needed: Forklifts, electric hand jacks, manual hand jacks, plastic wrap (IF APPLICABLE)
HHT'S equipment available, dibbs hand helds for information and printing labels
Make envelopes for each category. Make ESL's plastic bags (3) for each category *USE CURRENT STORE LAYOUT *
Flag all deletes and Pull all deletes from shelves (Prior to reset)
From label listing file (OFF SHELF)
USE PLANOGRAMS BASED ON STORE SIZE OR CATEGORY CLASS AS A GUIDE, PULL ONLY PRODUCTS ON THE POG,
PULL ALSO S AND REGIONAL PRODUCTS LABEL PRODUCT S OR R.
Pull 3-pull products for reset (DSD products also) Use other milk crates, boxes and produce bins OTHER THAN
pull down material saved. Pallets also can be use for bulk products
Pull 3-pull products (BY PLANOGRAM BY EACH SHELF exp. Shelf 1, Shelf 2) LABEL BOX BY SHELF)
Palletize 3-pull by category and new aisle
Order new products for reset *Print labels or make ESL's from label listing for new products*
From label listing file (NEED TO ORDER)
ESL'S, If you are having a full shelving reset, Make sure (ALL RAILS SHOULD BE PULL DOWN PRIOR TO RESET)
PULL RAILS BY DEGREE (CLEAN) AND ATTACH ESL'S BACK TO SHELF WITH APPORVED PACKING SCOTCH TAPE
SEPARATE ALL RAILS BY DEGREE * USE PRODUCE BINS*
ESL'S WILL BE PULL DOWN PRIOR TO THE PULL DOWN OF PRODUCTS
Put in heat ticket for CARTS for (2 days ) to have ESL's display UPC's instead of price to expedite the reset or
(POC) Aldo Conqiu (Store Operations)
Check in Shelving (USE PAPERWORK IN BOX LABELED "OPEN ME FIRST") ref.Guide to Shelving
Store gondola peg backboards and particle board in warehouse, Organize shelving by 26", 24" etc. (Write size on pallet*left and right*)
Order 3-pull (NIS's to complete 3- pull)
Sales Reset Team will bring all current planograms and expansions (Store Specific POG's)
Coordinate installation w/ contract installer
Equipment, staging area for build, entry and exit of equipment,
Store cleared out for reset
end caps, display pallets, merchandisers, alcove, and cueing line displays all remove off of sales floor
Create new "Customer Store Directory" layout prior to reopening for customers
Final store layouts will be sent you on the last day of the reset by the Reset Specialist
2015-11-12