## Sheet1
STORE RESET SCHEDULE FOR 2018 INITIAL DATE: 8/3/2017 REVISION NUMBER: 4 REVISION DATE: 3/21/2018
DATES | STORE | PROJECT | PROJECTED START / END DATE | TYPE OF SET | SHELVING | OTHER INFO | *LEAD
JAN. 1 - JAN. 6
JAN. 8 - JAN.13
JAN. 15 | [5 empty] | MLK DAY
JAN. 18 - JAN. 21 | CAMP HUMPHREYS, KR (K3) | NEW STORE | 2014 - 3/30/2018 | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | FULL SHELVING |  | *Darnell/Harry
JAN. 22 | SEYMOUR JOHNSON, NC (K3) | CANCELED |  | FROZEN |  |  | *Lisa
JAN. 24 - JAN. 25 | FORT BRAGG NORTH, NC (K4) | CANCELED |  | FROZEN |  |  | *Michelle
FEB. 04 | NO RESET |  |  |  |  | SUPER BOWL
FEB.11 - FEB. 13 | NO RESET
FEB. 16 - FEB. 18 | NO RESET
FEB.19 | NO RESET |  |  |  |  | PRESIDENT'S DAY
FEB.20 | YUMA MCAS, AZ (K1) | CANCELED |  | FROZEN |  |  | *Iveena
MAR. 03 - MAR. 05 | NO RESET
MAR. 10 - MAR. 12 | VANCE, OK (K1) | 2016 STORE / SHELVING |  | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | PARTIAL SHELVING | SAT PULL DOWN | *Michelle
MAR. 18 - MAR. 20 | NO RESET
MAR. 25 - MAR. 27 | COLUMBUS MOVED
APR. 01 | NO RESET |  |  |  |  | EASTER
APR. 08 - APR.10 | COLUMBUS, MS (K2) | SUSTAINMENT | Completed | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | PARTIAL UPPERS | SUN PULL DOWN | *Lisa/Chanell
APR. 08 - APR.10 | DAVIS MONTHAN, AZ (K4) | 2016 STORE / SHELVING |  | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | FULL SHELVING | SUN PULL DOWN | *Harry/Dave
APR. 21 - APR. 23 | SMOKEY POINT, WA (K2) | SUSTAINMENT | 9/12/2016 - 1/7/2018 (62%) | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | PARTIAL UPPERS | SAT PULL DOWN | *Michelle
APR. 22 - APR. 24 | FORT EUSTIS | DAX / IM DEPLOYMENT |  | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | PARTIAL UPPERS | SUN PULL DOWN | *Darnell/Dave
APR. 26 - APR. 28 | FAIRCHILD, WA (K3) | SOS REQUESTED |  | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | PARTIAL SHELVING | THURS PULL DOWN | *Harry/Michelle
MAY. 06 - MAY. 08 | FORT HUACHUCA, AZ (K3) | SUSTAINMENT | 11/15/2016 - 10/15/2017 | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | FULL SHELVING | SUN PULL DOWN | * Lisa/Harry
MAY. 13 | NO RESET |  |  |  |  | MOTHER'S DAY
MAY. 20 - MAY.22 | TYNDALL, FL (K3) | SUSTAINMENT | 1/23/2015 - 9/17/2017 (62%) | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | FULL SHELVING | SUN PULL DOWN | *Harry/Darnell
MAY. 23 - MAY.24 | MacDILL, FL (K3) |  |  | FROZEN |  |  | *Darnell
MAY. 28 | NO RESET |  |  |  |  | MEMORIAL DAY
JUN. 03 - JUN. 05 | NO RESET
JUN. 9 - JUN. 11 | F.E. WARREN, WY (K1) | SUSTAINMENT | 7/15/2015 - 11/25/2017 (93%) | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | PARTIAL UPPERS | SAT PULL DOWN | *Michelle
JUN. 17 | NO RESET |  |  |  |  | FATHER'S DAY
JUN. 24 - JUN. 26 | HILL AFB, UT (K3) | 2016 STORE / SHELVING |  | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | PARTIAL SHELVING | SUN PULL DOWN | *Lisa/Michelle
JUL. 04 | NO RESET |  |  |  |  | FORTH OF JULY
JUL. 08 - JUL. 10 | FORT WAINWRIGHT, AK (K2) | CAO UPGRADE / AD |  | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | PARTIAL SHELVING | SUN PULL DOWN | *Darnell/Dave
JUL. 15 - JUL. 17 | NO RESET
JUL.22 - JUL. 24 | LOS ANGELES, CA (K2) | SUSTAINMENT | 7/15/2015 - 12/14/2017 (90%) | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | FULL SHELVING | SUN PULL DOWN | *Harry/Michelle
JUL.29 - JUL. 31 | NO RESET
AUG. 05 - AUG. 07 | NO RESET
AUG.12 - AUG. 14 | NO RESET
AUG. 16 - AUG. 18 | ATSUGI. JP (K2) | R-22 REF |  | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | PARTIAL UPPERS | THURS PULL DOWN | *Darnell/Lisa
AUG. 26 - AUG. 28 | SAGAMIHARA, JP (K2) | SUSTAINMENT | Completed | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | PARTIAL UPPERS | SUN PULL DOWN | *Darnell/Lisa
SEPT. 03 | NO RESET |  |  |  |  | LABOR DAY
SEPT. 09 - SEPT. 11 | PORT HUENEME, CA (K2) | SUSTAINMENT | 7/15/2015 - 12/2/2017 (80%) | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | FULL SHELVING | SUN PULL DOWN | *Lisa/Harry
SEPT. 16 - SEPT. 18 | NO RESET
SEPT. 24 - SEPT. 26 | VILSECK, GR (D) | 2016 STORE / SHELVING |  | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | FULL SHELVING | TUES PULL DOWN | *Darnell/Michelle/dave
SEP. 29 - OCT. 1 | WIESBANDEN,GR (D) | 2016 STORE / SHELVING |  | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | FULL SHELVING | SAT PULL DOWN | *Darnell/Michelle
OCT. 08 | NO RESET |  |  |  |  | COLUMBUS DAY
OCT. 12 - OCT. 14 | FORT IRWIN, CA (K2) | SUSTAINMENT | 1/19/2016 - 11/30/2017 (62%) | DRY/CHILL DAIRY/PREPACKAGE MEAT/FRZ | FULL SHELVING | FRI PULL DOWN | *Michelle/Lisa
OCT. 16 - OCT. 18 | NO RESET
OCT. 28 - OCT. 30 | NO RESET
NO SET
NOV. 04 - NOV. 06 | NO RESET
NOV. 11 - NOV. 13 | NO RESET
NOV. 18 - NOV. 20 | NO RESET
NOV. 25.- NOV. 27 | NO RESET
`
DEC. 02 - DEC. 04 | NO RESET
DEC. 09 - DEC. 11 | NO RESET
DEC. 16 - DEC. 18 | NO RESET
DEC. 23.- DEC. 25 | NO RESET
HIGHLIGHTS: | [6 empty] | 2018-04-18
NEW STORE
DUE SHELVING 18
REVOVATON
2016 STORES
FROZEN SETS ONLY
DAX / IM DEPLOYMENT
Notes:
STORES REMOVED FROM 2018 SCHEDULE*
Bangor, ME*
Meridian, MS*
Barstow, CA*
Note on F26: Request shelving from other stores.